| Task name | Parent task | Epic | List | Status | Priority | Estimate | Assignee role | Dependency | Due suggestion | Description | Acceptance criteria |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Define MVP scope |  | Product & Planning | Backlog | Ready | Urgent | 4h | Product Lead | Proposal | Day 1 | Chốt phạm vi MVP theo proposal | Có tài liệu in-scope/out-of-scope rõ ràng |
| Define out-of-scope |  | Product & Planning | Backlog | Ready | High | 2h | Product Lead | Define MVP scope | Day 1 | Liệt kê phần không làm trong MVP | Có danh sách out-of-scope thống nhất |
| Write product brief |  | Product & Planning | Backlog | Ready | High | 3h | Product Lead | Define MVP scope | Day 1 | Viết brief sản phẩm 1 trang | Brief có mục tiêu, users, value, MVP, risks |
| Define success metrics |  | Product & Planning | Backlog | Ready | Medium | 2h | Product Lead | Write product brief | Day 1 | Xác định chỉ số MVP | Có KPI và điều kiện demo thành công |
| Map entry gate flow |  | Product & Planning | Backlog | Ready | Urgent | 4h | Solution Architect | Define MVP scope | Day 1 | Vẽ flow cổng vào | Có success/fail path đầy đủ |
| Map exit gate flow |  | Product & Planning | Backlog | Ready | Urgent | 4h | Solution Architect | Define MVP scope | Day 1 | Vẽ flow cổng ra | Có success/fail path đầy đủ |
| Map admin flow |  | Product & Planning | Backlog | Ready | High | 3h | Solution Architect | Define MVP scope | Day 1 | Vẽ flow dashboard/admin | Có login, logs, whitelist flow |
| Create architecture note |  | Architecture & Platform | Architecture | Ready | Urgent | 6h | Solution Architect | Map entry gate flow | Day 2 | Viết architecture note MVP | Có module map, data flow, integration strategy |
| Define service boundaries |  | Architecture & Platform | Architecture | Ready | High | 3h | Tech Lead | Create architecture note | Day 2 | Chia module backend rõ ràng | Không mơ hồ responsibility |
| Define hardware integration strategy |  | Architecture & Platform | Architecture | Ready | High | 3h | Solution Architect | Create architecture note | Day 2 | Chốt simulator-first + adapter design | Có contract hardware/LPR rõ |
| Design ERD |  | Architecture & Platform | Database Design | Ready | Urgent | 8h | Backend Dev | Map entry gate flow | Day 2 | Thiết kế database schema v1 | ERD đủ cho transactions, payments, tickets, plate_reads, logs |
| Define enums and state machine |  | Architecture & Platform | Database Design | Ready | Urgent | 4h | Backend Dev | Design ERD | Day 2 | Chốt status giao dịch/gate event | Enum không xung đột, đủ success/fail |
| Draft API contract |  | Architecture & Platform | API Design | Ready | High | 6h | Backend Dev | Create architecture note | Day 2 | Liệt kê endpoint MVP | Có request/response cơ bản |
| Create repository |  | Project Setup | Backend | Ready | High | 1h | Tech Lead | Naming agreed | Day 1 | Tạo GitHub repo chính | Repo tồn tại, naming đúng |
| Add branch rules |  | Project Setup | Backend | Backlog | High | 1h | Tech Lead | Create repository | Day 1 | Cấu hình main/develop/protection | Không push thẳng vào main |
| Add issue and PR templates |  | Project Setup | Backend | Backlog | Medium | 2h | Tech Lead | Create repository | Day 1 | Thêm template chuẩn | Có bug/feature/task issue template + PR template |
| Setup CI workflow |  | Project Setup | DevOps | Backlog | Medium | 3h | DevOps | Create repository | Day 2 | Thêm lint/test CI cơ bản | CI chạy khi mở PR |
| Setup backend skeleton |  | Project Setup | Backend | Ready | Urgent | 4h | Backend Dev | Create repository | Day 1 | Dựng FastAPI skeleton | Chạy local OK, health endpoint OK |
| Setup frontend skeleton |  | Project Setup | Frontend | Ready | High | 4h | Frontend Dev | Create repository | Day 1 | Dựng React app shell | Chạy local OK |
| Setup Docker Compose |  | Project Setup | DevOps | Backlog | High | 3h | DevOps | Setup backend skeleton | Day 2 | Tạo docker-compose cho app + db | docker compose up chạy được |
| Add env management |  | Project Setup | DevOps | Backlog | High | 2h | DevOps | Setup Docker Compose | Day 2 | Tạo .env.example và config | App đọc env đúng |
| Implement admin login JWT |  | Backend Foundation | Backend | Ready | Urgent | 8h | Backend Dev | Design ERD | Day 3 | Login admin bằng JWT | Login được, token hợp lệ |
| Implement role guard |  | Backend Foundation | Backend | Backlog | High | 4h | Backend Dev | Implement admin login JWT | Day 3 | Guard role cho admin/operator | Endpoint protected theo role |
| Add password hashing |  | Backend Foundation | Backend | Backlog | High | 2h | Backend Dev | Implement admin login JWT | Day 3 | Hash và verify password | Không lưu plain text |
| Add audit log for auth |  | Backend Foundation | Backend | Backlog | Medium | 3h | Backend Dev | Implement admin login JWT | Day 3 | Log auth attempts | Login success/fail được log |
| Create initial migrations |  | Backend Foundation | Backend | Ready | Urgent | 6h | Backend Dev | Design ERD | Day 3 | Tạo migration v1 | DB migrate thành công |
| Add transaction module |  | Backend Foundation | Backend | Backlog | High | 6h | Backend Dev | Create initial migrations | Day 4 | CRUD/service cho transaction | Tạo/đọc/cập nhật transaction được |
| Add payment module |  | Backend Foundation | Backend | Backlog | High | 5h | Backend Dev | Add transaction module | Day 4 | Xử lý payment records | Payment record tạo đúng |
| Add ticket module |  | Backend Foundation | Backend | Backlog | High | 5h | Backend Dev | Add transaction module | Day 4 | Quản lý ticket/card | Ticket link đúng transaction |
| Add gate event module |  | Backend Foundation | Backend | Backlog | High | 5h | Backend Dev | Add transaction module | Day 4 | Log sự kiện cổng | Event được ghi đủ |
| Add whitelist module |  | Backend Foundation | Backend | Backlog | High | 4h | Backend Dev | Create initial migrations | Day 4 | API whitelist CRUD | Plate whitelist lookup hoạt động |
| Build vehicle detection handler |  | Entry Gate MVP | Backend | Backlog | High | 4h | Backend Dev | Add gate event module | Day 5 | Nhận event detect xe | Event detect được tạo và log |
| Build plate capture and LPR adapter |  | Entry Gate MVP | Backend | Backlog | Urgent | 8h | Backend Dev | Build vehicle detection handler | Day 5 | Adapter gọi LPR service/mock | Lưu plate read + confidence |
| Build whitelist check flow |  | Entry Gate MVP | Backend | Backlog | High | 4h | Backend Dev | Add whitelist module | Day 5 | Check biển số trong whitelist | Free-access flow chạy đúng |
| Build prepaid payment flow |  | Entry Gate MVP | Backend | Backlog | Urgent | 8h | Backend Dev | Add payment module | Day 6 | Xử lý student card/cash mock | Payment success/fail ghi nhận đúng |
| Build ticket issuance flow |  | Entry Gate MVP | Backend | Backlog | Urgent | 6h | Backend Dev | Add ticket module | Day 6 | Issue ticket sau payment/whitelist | Ticket được link transaction |
| Build barrier open logic |  | Entry Gate MVP | Backend | Backlog | High | 5h | Backend Dev | Build ticket issuance flow | Day 6 | Mở barrier khi hợp lệ | Không mở barrier nếu chưa đủ điều kiện |
| Build entry logging flow |  | Entry Gate MVP | Backend | Backlog | High | 3h | Backend Dev | Build barrier open logic | Day 6 | Ghi log đầy đủ cổng vào | Event trace đầy đủ |
| Setup admin login screen |  | Admin Dashboard MVP | Frontend | Backlog | Medium | 4h | Frontend Dev | Setup frontend skeleton | Day 5 | Trang login admin | Gọi API login thành công |
| Build dashboard shell |  | Admin Dashboard MVP | Frontend | Backlog | Medium | 5h | Frontend Dev | Setup admin login screen | Day 6 | Layout dashboard | Có route và layout cơ bản |
| Build summary API/UI |  | Admin Dashboard MVP | Frontend | Backlog | Medium | 6h | Frontend Dev | Add transaction module | Day 7 | KPI summary | Hiển thị total vehicles/revenue/occupancy |
| Build transaction log page |  | Admin Dashboard MVP | Frontend | Backlog | Medium | 6h | Frontend Dev | Add gate event module | Day 7 | Trang transaction logs | Filter và xem log được |
| Build whitelist management page |  | Admin Dashboard MVP | Frontend | Backlog | Medium | 6h | Frontend Dev | Add whitelist module | Day 8 | CRUD whitelist UI | Add/edit/remove hoạt động |
| Build hardware status page |  | Admin Dashboard MVP | Frontend | Backlog | Low | 4h | Frontend Dev | Define hardware integration strategy | Day 9 | Trạng thái thiết bị mock | Hiển thị online/offline |
| Build ticket/card read flow |  | Exit Gate MVP | Backend | Backlog | Urgent | 6h | Backend Dev | Add ticket module | Day 8 | Read ticket/card tại cổng ra | Lấy đúng transaction |
| Build exit plate capture |  | Exit Gate MVP | Backend | Backlog | Urgent | 6h | Backend Dev | Build plate capture and LPR adapter | Day 8 | Capture plate cổng ra | Plate read exit được tạo |
| Build plate rematch validation |  | Exit Gate MVP | Backend | Backlog | Urgent | 8h | Backend Dev | Build exit plate capture | Day 9 | So khớp plate entry/exit | Match/mismatch đúng logic |
| Build exit deny logic |  | Exit Gate MVP | Backend | Backlog | High | 4h | Backend Dev | Build plate rematch validation | Day 9 | Từ chối exit khi invalid | Barrier không mở khi mismatch |
| Build valid exit barrier flow |  | Exit Gate MVP | Backend | Backlog | High | 4h | Backend Dev | Build plate rematch validation | Day 9 | Mở barrier nếu valid exit | Transaction complete đúng |
| Build exit logging flow |  | Exit Gate MVP | Backend | Backlog | High | 3h | Backend Dev | Build valid exit barrier flow | Day 9 | Log đầy đủ cổng ra | Audit trace hoàn chỉnh |
| Setup unit test base |  | Quality & Release | Test Cases | Backlog | Medium | 3h | QA / Backend Dev | Setup backend skeleton | Day 10 | Base test framework | Chạy được test đầu tiên |
| Setup integration test base |  | Quality & Release | Test Cases | Backlog | High | 4h | QA / Backend Dev | Build entry logging flow | Day 10 | Integration test cho core flow | Có ít nhất 1 test pass |
| Create manual smoke checklist |  | Quality & Release | Test Cases | Backlog | High | 2h | QA | Build dashboard shell | Day 10 | Checklist smoke test | Có checklist dùng được |
| Setup staging deploy |  | Quality & Release | Staging | Backlog | Medium | 6h | DevOps | Setup Docker Compose | Week 2 end | Deploy staging đầu tiên | Staging truy cập được |
| Create rollback plan |  | Quality & Release | Release Checklist | Backlog | Medium | 2h | DevOps | Setup staging deploy | Week 2 end | Kế hoạch rollback | Có step rollback rõ ràng |